## Gantt Chart
Miromio Café Online Menu & Ordering System — WBS & 6-Week Gantt Chart
Project Duration: 6 Weeks (Sep 1 – Oct 8, 2026) ¦ Target Deliverable: Online Menu & Ordering System
WBS ID | Task Name | Level | Deliverable | Duration (Weeks) | Start Week | End Week | 1w | 2w | 3w | 4w | 5w | 6w
[7 empty] | Sep 1–7 | Sep 8–14 | Sep 15–21 | Sep 22–28 | Sep 29–Oct 5 | Oct 6–8
1.0 | Customer | 1 | Customer activities | 5 | 1 | 6 | ■ | ■ | ■ | ■ | ■ | ■
1.1 | View Menu | 2 | Menu viewed | 1 | 1 | 1 | ■
1.2 | View Café Information | 2 | Café information viewed | 1 | 1 | 1 | ■
1.3 | Place Order | 2 | Order placed | 1 | 2 | 2 |  | ■
1.4 | View Order Status | 2 | Order status viewed | 2 | 4 | 5 |  |  |  | ■ | ■
1.5 | Receive Ready Notification | 2 | Ready notification received | 2 | 5 | 6 |  |  |  |  | ■ | ■
2.0 | Online Ordering System | 1 | System processes | 5 | 1 | 6 | ■ | ■ | ■ | ■ | ■ | ■
2.1 | Display Menu & Café Information | 2 | Menu and café information displayed | 1 | 1 | 1 | ■
2.2 | Receive & Record Order | 2 | Order recorded | 1 | 2 | 2 |  | ■
2.3 | Check Order | 2 | Order checked | 1 | 3 | 3 |  |  | ■
2.4 | Send Order to Café Staff | 2 | Order sent to staff | 1 | 3 | 3 |  |  | ■
2.5 | Send Ready Notification | 2 | Ready notification sent | 2 | 5 | 6 |  |  |  |  | ■ | ■
3.0 | Café Staff | 1 | Café staff activities | 5 | 1 | 5 | ■ | ■ | ■ | ■ | ■
3.1 | Manage Prices/Menu | 2 | Prices and menu managed | 1 | 1 | 1 | ■
3.2 | Receive & Review Order | 2 | Order reviewed | 1 | 3 | 3 |  |  | ■
3.3 | Prepare Order | 2 | Order prepared | 2 | 4 | 5 |  |  |  | ■ | ■
3.4 | Update Order Status | 2 | Order status updated | 1 | 5 | 5 |  |  |  |  | ■
Legend | Main activity | Subtask | Project group